## Team Summary
EDPA 1.9.0 — PI-2026-1.1
Project: Medical Platform & Datovy e-shop
Person | Role | FTE | Capacity (h) | Derived (h) | Items | OK
J. Urbanek | Arch | 0.5 | 40 | 40 | 1 | ✓
O. Tuma | DevSecOps | 1 | 80 | 80 | 2 | ✓
Turyna | Dev | 0.75 | 60 | 60 | 2 | ✓
Matousek | Dev | 0.75 | 60 | 60 | 2 | ✓
PM Partner | PM | 0.5 | 40 | 0 | 0 | ✓
Sr Dev MC | Dev | 0.5 | 40 | 40 | 1 | ✓
DB Spec MC | Dev | 0.5 | 40 | 0 | 0 | ✓
DevOps MC | Dev | 0.25 | 20 | 0 | 0 | ✓
UX Designer | UX | 0.25 | 20 | 0 | 0 | ✓
TOTAL |  |  | 400 | 280 | 8

## Item Costs
EDPA 1.9.0 — PI-2026-1.1 — Per-Item Allocation
Item | Level | JS | Person | CW | Score | Ratio | Hours
S-201 | Story | 5 | J. Urbanek | 0.3 | 1.5 | 100.0% | 40
S-202 | Story | 3 | O. Tuma | 1 | 3 | 37.5% | 30
S-203 | Story | 5 | O. Tuma | 1 | 5 | 62.5% | 50
S-201 | Story | 5 | Turyna | 1 | 5 | 87.0% | 52.17
S-202 | Story | 3 | Turyna | 0.25 | 0.75 | 13.0% | 7.83
S-203 | Story | 5 | Matousek | 0.6 | 3 | 50.0% | 30
S-204 | Story | 3 | Matousek | 1 | 3 | 50.0% | 30
S-204 | Story | 3 | Sr Dev MC | 0.25 | 0.75 | 100.0% | 40